## Tasks and Timeline
Sauce & Spoon Project Plan
| Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| Vendor timeline and deliverables schedule |  |  |  | 4 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
TRAINING group |  |  |  |  | 0 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
| Training preparation |  |  |  | 6
| Pre-training meeting to introduce tablets and changes to staff - location 1 | trainings will be separate, in project plan need to schedule it in bigger detail |  |  | 0.83333
| Pre-training meeting to introduce tablets and changes to staff - location 2 | trainings will be separate, in project plan need to schedule it in bigger detail |  |  | 1.3333
| Train key staff members at each location - location 1 | trainings will be separate, in project plan need to schedule it in bigger detail |  |  | 1.3333
| Train key staff members at each location - location 2 | trainings will be separate, in project plan need to schedule it in bigger detail |  |  | 1.3333
| Separate trainings at each location - location 1 | trainings will be separate, in project plan need to schedule it in bigger detail |  |  | 1.3333
| Separate trainings at each location - location 2 | trainings will be separate, in project plan need to schedule it in bigger detail |  |  | 1.3333
| milestone: TRAINING complete |  |  |  | 0 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
TABLETS preparation | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
| Decide what tablet model to buy | Can be a multiple tasks if we will want to test it |  |  | 6 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
| Shipping | Low probability that shipping will come late or the goods will be damaged Shipment got delayed by storm - tablets are arriving from a different place now, estimation recalculated accordingly |  |  | 10
| Menu items and coupon values preparation | Very high probability of wrong estimations, need to manage closely |  |  | 11.6667
| Designer mock ups |  |  |  | 1
| Decide how to install tablets |  |  |  | 2
| Tablets software POS integration |  |  |  | 0.66667
| Tablets POS upgrade (maybe not needed) | We need to check whether this step is needed ASAP |  |  | 4
| Prepare one tablet instalation in location North |  |  |  | 2.3333 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
| Prepare one tablet instalation in location Downtown |  |  |  | 1.8333 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
milestone: TABLETS preparation complete | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
TABLETS onsite works | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
| Test connection to existing databases and systems in location North |  |  |  | 1.8333 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
| Test connection to existing databases and systems in location Downtown |  |  |  | 1.8333 | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
| Get approval from North |  |  |  | 1.3333
| Get approval from Downtown |  |  |  | 1.3333
| Select and book an electrician vendor |  |  |  | 2.3333
| Vendor electricity connection | This is actually 4 times half a day, restaurants will be closed twice for half a day each |  |  | 5
| milestone: TABLETS onsite installation complete |  |  |  | 0
UAT group |  |  |  |  | 0
| UX testing - from case study |  |  |  | 2.3333
| Tablet place testing - from case study |  |  |  | 2.3333
| Each GM to have a staff meeting to present changes and discuss impacts on staff |  |  |  | 2.3333
| Schedule a test run at each location |  |  |  | 2.3333
| Run a test run at each location and collect feedback |  |  |  | 2.3333
| Feedback changes buffer |  |  |  | 5
| milestone: UAT testing complete |  |  |  | 0
Post release group
| Upload software to new model |  |  |  | 1
| Swap tablets for new model - locality 1 | This should be only tablet change, but we need to upload a new software before as well |  |  | 1.3333
| Swap tablets for new model - locality 2 | This should be only tablet change, but we need to upload a new software before as well |  |  | 1.3333
milestone: tablet change complete

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Vendor timeline and deliverables schedule |  | 4 | 2 | 4 | 6 | M
0
TRAINING group |  | 0
Training preparation |  | 6 | 5 | 6 | 7 | H
Pre-training meeting to introduce tablets and changes to staff - location 1 | trainings will be separate, in project plan need to schedule it in bigger detail | 0.83333 | 1 | 0.5 | 1 | L
Pre-training meeting to introduce tablets and changes to staff - location 2 | trainings will be separate, in project plan need to schedule it in bigger detail | 1.3333 | 1 | 1 | 2 | L
Train key staff members at each location - location 1 | trainings will be separate, in project plan need to schedule it in bigger detail | 1.3333 | 1 | 1 | 2 | H
Train key staff members at each location - location 2 | trainings will be separate, in project plan need to schedule it in bigger detail | 1.3333 | 1 | 1 | 2 | H
Separate trainings at each location - location 1 | trainings will be separate, in project plan need to schedule it in bigger detail | 1.3333 | 1 | 1 | 2 | L
Separate trainings at each location - location 2 | trainings will be separate, in project plan need to schedule it in bigger detail | 1.3333 | 1 | 1 | 2 | L
milestone: TRAINING complete |  | 0 | 0 | 0 | 0 | H
0
TABLETS group |  | 0
Decide what tablet model to buy | Can be a multiple tasks if we will want to test it | 6 | 3 | 5 | 10 | M
Shipping | Low probability that shipping will come late or the goods will be damaged Shipment got delayed by storm - tablets are arriving from a different place now, estimation recalculated accordingly | 10 | 8 | 9 | 13 | M
Menu items and coupon values preparation | Very high probability of wrong estimations, need to manage closely | 11.6667 | 5 | 10 | 20 | M
Designer mock ups |  | 1 | 0.5 | 0.5 | 2 | M
Decide how to install tablets |  | 2 | 1 | 2 | 3 | H
Tablets software POS integration |  | 0.66667 | 0.5 | 0.5 | 1 | L
Tablets POS upgrade (maybe not needed) | We need to check whether this step is needed ASAP | 4 | 3 | 4 | 5 | L
Prepare one tablet instalation in location North |  | 2.3333 | 1 | 2 | 4 | H
Prepare one tablet instalation in location Downtown |  | 1.8333 | 0.5 | 1 | 4 | H
Test connection to existing databases and systems in location North |  | 1.8333 | 0.5 | 1 | 4 | H
Test connection to existing databases and systems in location Downtown |  | 1.8333 | 0.5 | 1 | 4 | H
Get approval from North |  | 1.3333 | 1 | 1 | 2 | H
Get approval from Downtown |  | 1.3333 | 1 | 1 | 2 | H
Select and book an electrician vendor |  | 2.3333 | 1 | 2 | 4 | M
Vendor electricity connection | This is actually 4 times half a day, restaurants will be closed twice for half a day each | 5 | 4 | 5 | 6 | M
milestone: TABLETS installation complete |  | 0
0
UAT group |  | 0
UX testing - from case study |  | 2.3333 | 1 | 2 | 4 | M
Tablet place testing - from case study |  | 2.3333 | 1 | 2 | 4 | M
Each GM to have a staff meeting to present changes and discuss impacts on staff |  | 2.3333 | 1 | 2 | 4 | M
Schedule a test run at each location |  | 2.3333 | 1 | 2 | 4 | M
Run a test run at each location and collect feedback |  | 2.3333 | 1 | 2 | 4 | M
Feedback changes buffer |  | 5 | 5 | 5 | 5 | M
milestone: UAT testing complete |  | 0
Upload software to new model |  | 1 | 1 | 1 | 1 | M
Swap tablets for new model - locality 1 | This should be only tablet change, but we need to upload a new software before as well | 1.3333 | 1 | 1 | 2 | M
Swap tablets for new model - locality 2 | This should be only tablet change, but we need to upload a new software before as well | 1.3333 | 1 | 1 | 2 | M
0
0
0
0

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
tabletop service speed up | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ | 2021-12-07
tablet usability research | https://www.system-concepts.com/case-studies/tablet-usability-research-case-study/ | 2021-12-07
just eat case study | https://www.system-concepts.com/wp-content/uploads/2019/03/SCL_CS_JustEat_2019.pdf | 2021-12-07

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Faster, more efficient experience | average delivery time | is it below eight minutes for appetizers? | average delivery time | FALSE
| average delivery time | is it below 13.5 minutes for entrees? | average delivery time | FALSE
| quicker check-out | is it done in one minute or less? | checkout time | FALSE
| technical issues tablets report | does less than 5% of customers report technical issues each week? | technical issues report | FALSE
| order accuracy | is the order accuracy 98% or higher? | order accuracy | FALSE
| decreased customer wait time in the lobby | is the average wait time of ten minutes or less before customers are seated? | average wait time | FALSE
General, reccuring |  | Are customers having a better dining experience with the tablets? | satisfaction level | FALSE
|  | Are customers receiving the correct orders? | orders | FALSE
|  | Does the waitstaff enjoy using the tablets? | survey | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Faster, more efficient experience | Dining experience | Are customers having a better dining experience with the tablets? | Do you have a better dining experience with the tablets or would you prefer it without it? | Yes/No | yes | no
|  |  | Did you experience any issue with the tablet? | Yes/No | yes | no
|  |  | Is it true that your experince seems more seemless with the tablet? | True/False | true | false
|  |  | Did you have any navigation issue? | Yes/No | yes | no
|  | Is customer retention improving? | Have you visited our restaurant in the past? | Yes/No | yes | no
|  |  | Do you plan to visit the restaurant again? | Yes/No | yes | no
|  |  | Would you recommend a restaurant to a friend? | Yes/No | yes | no
|  |  | If yes, how many people do you expect would come to have a dinner with them? | Scaled
|  | What is the segment client would like the tablets the most? | What groups do you think are more likely to preffer tablets? | Multiple choice | single person | small group | medium group | big group
|  | Is the wait time satisfactory? | How would you describe your table waiting time? | Multiple choice | none | great | normal | terrible
|  |  | How would you describe your appetizer waiting time? | Multiple choice | none | great | normal | terrible
|  |  | How would you describe your entrees waiting time? | Multiple choice | none | great | normal | terrible
|  |  | How would you describe your overall waiting time? | Multiple choice | none | great | normal | terrible
|  | Are clients generaly satisfied? | On a scale from 0 to 10, how are you satisfied with our NEW offers and services? | Scaled
|  |  | On a scale from 0 to 10, how were you satisfied with our OLD offers and services? | Scaled
|  |  | Is there anything that you were dissatisfied with? | Open-ended | open-ended