## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | 40% of guests rated their experience as a 4 out of 5 | Data point 14. from the customer survey | monitor
Customers | Went well | 56% of guests received their order within 20 minutes | Data point 8. from the customer survey | monitor
Customers | Went well | 72% of guests rated their tablet experience above average | Data point 3. from the customer survey | monitor
Customers | Needs improvement | 22% of guests rated navigation as mediocre or difficult | Data point 5. from the customer survey | needs further improvement, schedule meeting
Customers | Needs improvement | 26% of guests rated difficulty to order as mediocre or difficult | Data point 6. from the customer survey | needs further improvement, schedule meeting
Customers | Needs improvement | 54% of guests waited more than 15 minutes for their table | Data point 7. from the customer survey | GMs to send ideas to process improvement
Project team | Went well | All tablets sucesfully installed at both locations | Retrospective review meeting notes | none
Project team | Went well | Customers were able to use tablets and payments easily | Retrospective review meeting notes | none
Project team | Went well | Vendor communication was clear with regular statuses | Retrospective review meeting notes | none
Project team | Needs improvement | Table turn time is below expectation | Retrospective review meeting notes | GMs to send ideas to process improvement
Project team | Needs improvement | Incorrect orders that had to be sent back | Retrospective review meeting notes | GMs to send ideas to process improvement (kitchen operations mostly)
Project team | Needs improvement | Possibility of technical issue that affects order accuracy | Retrospective review meeting notes | Seidou to adress it first